## Sheet1
STT | week | Deadline | Tasks
1 | 1 | 2018-12-01 | phân tích thiết kế xong chức năng, thiết kế hệ thống, db, sơ đồ use case, lựa chọn xong template
2 | 2 | 2018-12-15 | Nghiên cứu .net core, hoành thành Front end, chức năng login, show thông tin công ty
3 | 2 | 2018-12-29 | Hoàn thành chức năng cơ bản web site, cho phép đăng nhập bằng fb, google, view cty, dang job cty, review, comment, ưng tuyển cty, tích hợp google map để chỉ đường đến công ty
Hoàn thành giai đoạn 1 phát triển MVP
4 | 8 | 2019-02-02 | Hoàn thiện giao diện, thêm chức năng tìm kiếm theo khu vực, hiển thị db lên bản đồ, đo khoảng cách trên bản đồ, nghiên cứu phát triển trên nền ứng dụng điện thoại
Phát triển các tính năng an toàn, quét lỗ hổng bảo mật
Hoàn thành giai đoạn 2 phát triển, sản phẩm chạy nuột trên web
Detail Tasks |  | Task Name
| PTTK: | Scope | 4 days
Determine project scope
Define preliminary resources
|  | Analysis/Software Requirements | 7 days
Conduct needs analysis
Draft preliminary software specifications
Develop preliminary budget
Incorporate feedback on software specifications
Develop delivery timeline
Design
Develop functional specifications
Develop prototype based on functional specifications
Review functional specifications
Incorporate feedback into functional specifications
|  | Development | 14 days
Review functional specifications
Identify modular/tiered design parameters
Develop code
Developer testing (primary debugging)
Testing
Develop unit test plans using product specifications
Develop integration test plans using product specifications
Unit Testing
Review modular code
Test component modules to product specifications
Identify anomalies to product specifications
Modify code
Re-test modified code
Unit testing complete
Integration Testing
Test module integration
Identify anomalies to specifications
Modify code
Re-test modified code
Integration testing complete
Training
Develop training specifications for end users
Develop training specifications for helpdesk support staff
Identify training delivery methodology (computer based training, classroom, etc.)
Develop training materials
Conduct training usability study
Finalize training materials
Develop training delivery mechanism
Training materials complete
Documentation
Develop Help specification
Develop Help system
Review Help documentation
Incorporate Help documentation feedback
Develop user manuals specifications
Develop user manuals
Review all user documentation
Incorporate user documentation feedback
Documentation complete
Deployment
Determine final deployment strategy
Develop deployment methodology
Secure deployment resources
Train support staff
Deploy software
Deployment complete
Post Implementation Review
Document lessons learned
Distribute to team members
Create software maintenance team
Post implementation review complete
Software development template complete